# Kanch Innovative Technologies

# Proposal to Lusaka City Council (LCC)

## 1. Executive Summary

Kanch Innovative Technologies proposes a digital municipal certificate display system. Instead of paper certificates hung on walls, businesses will use a portrait E-Ink device that updates automatically when payments are made. Inspectors will use handheld scanners with colored maps (green/red) to target only non-compliant premises. GPS and open/closed sensors will ensure compliance.

## 2. Current Challenges

Businesses must queue for hard-copy certificates.

Paper certificates are easily forged or damaged.

Inspectors waste time entering compliant premises.

No real-time view of compliance across Lusaka.

## 3. Proposed Solution

LCC Portrait Display: 7.5"–10.1" E-Ink, displays business levy, fire certificate, health certificate, etc. Slides if multiple.

Wireless Power Adapter: portable charging.

LCC Inspector Scanner: colored map (green/red), direction finding, open/closed alerts.

GPS tracking: live location of all displays.

Open/closed sensor: detects when premises are opened/closed, alerts inspectors.

Central server: polls LCC payment API every 1–2 minutes, updates displays.

Command Dashboard: big screen for Director of Finance, Town Clerk, Mayor.

## 4. Benefits to LCC

Eliminate paper certificate printing and queueing.

Inspectors focus only on non-compliant businesses.

Real-time compliance map of Lusaka.

Reduce fraud and increase revenue.

Data-driven decision making.

## 5. Implementation Plan

| Phase | Activity | Duration | Cost (USD) |
| --- | --- | --- | --- |
| Phase 1 | Prototype & testing | 3 months | $40,000 |
| Phase 2 | Pilot with 500 businesses | 6 months | $150,000 |
| Phase 3 | Full rollout | 12 months | $800,000 |

## 6. Cost per Business

LCC Portrait Display + Adapter: ~$53–$80 USD. Inspector Scanner: ~$48–$74 USD per inspector. Monthly SaaS: $3 per business for server, updates, GPS, sensors.

## 7. Conclusion

Kanch Innovative Technologies is ready to partner with LCC to digitize municipal certificates and streamline compliance. We request a pilot program to demonstrate the system.